## Guide
Product Backlog:
- It is a priority list of user requirements to develop a software or an application.
- Product owner owns this document
- Product owner prioritize the user requirements based on the customer feedback or business value
- The user requirements are written in the form of user stories which are explained in detail
- The product backlog is like a repository that act as an input to the sprint backlog.
- In simple sentence, product backlog is simply a wish list for an application.
- Update the product backlog on regular basis
Sprint Backlog
- It is the subset of the product backlog
- Each sprint includes user stories from the product backlog
- Product owner sets the sprint goal for the team
- The team then pick the user stories to fulfill those goals
- The user stories that are moved to sprint are then owned by the scrum team
- It is important to put the sprint goals as static as possible.
- During sprint planning, the team pics the recently prioritized user stories from the product backlog.
- Spring backlog is an output of the sprint planning meeting
User Story
A user story is simply a description of a feature that is described in users own words. Therefore, it is extremely important to recognize the users. A user is the user of a system. When writing user stories, it is also beneficial to explain the business value first.
The user story are written as:
As a (user), I want to ..... so that ......
Examples:
As an administrator, i want to be able to create new user accounts.
As a student, I should be able to upload assignemtns in the Moodle.
As a student, I want to be able to change my password.
Example with business value (recommended)
In order to find the cheapest price, as a buyer i want to compare prices.
In order to check grades in quick time, as a student I want to be able to see all my grades in one page.
Story Points
- They are a unit of measures for expressing an estimate of the overall effort that is needed to implement a produc backlog item.
- The estimation is done by assigning a point value to each item.
- The raw values that is assigned is not important however the relative values matters.
- Let us assume that one of your story is assigend a vlaue 1 and other other story 2. The one with the value 2 means that it requires dobule effort that the story with the value 1. It means the value itself does not matter but the ratios matter.
- When deciding story points, you need to take into account the amount, complexity and any risk or uncertaninty in doing the work.

## ProductBacklog
Product Backlog - Vaalikone
User Stroy | Story Point(s) | Priority | Number meanings
as an admin I can add candidates | 4 | 5 | Low | Medium | High
as an admin I can edit candidates | 4 | 4 | 1 | 3 | 5
as an admin I can delete candidates | 2 | 3
as an admin I can add questions | 4 | 5
as an admin I can edit questions | 4 | 4
as an admin I can delete questions | 2 | 3
as an admin I can answer to candidates questions | 5 | 5
as an admin I can edit candidates questions | 5 | 4
as an admin I can see all the questions | 1 | 3
as an admin I can see all the candidates | 1 | 3
as an admin I can log out | 2 | 1
as an admin I can log in | 3 | 5

## sprint_planning_meetings
Spring Planning | Participants
Week 12 | Kaisa | Sonja | Jenna
2022-03-25 | Online | Online | Online | If physically present mark X
Week 13 | Kaisa | Sonja | Jenna
1.4.2022 klo 12 | Online | Online | Online
Week 14 | Kaisa | Sonja | Jenna
7.4.2022 klo 13 | Online | Online | Online
Week 15 | Kaisa | Sonja | Jenna
12.4.2022 klo 13.30 | Online | Online | Online
Esittely | Kaisa | Sonja | Jenna
13.4.2022 klo 16.40 | Online | Online | Online
Extra meeting | 10.4.2022 klo 11-14.30
Sprint Planning
- Sprint planning is done at the beginning of each sprint with the participation of the entire scrum team.
- During the sprint planning meeting, the scrum team decides what will be delivered at the end of the sprint by turning the highest priority features on the product backlog into detailed tasks.
- This process creates the sprint backlog.
- The sprint planning meeting focuses on answering two main questions:
1) What needs to be done? and
2) How will it be done?
The sprint goal is also defined during the sprint planning meeting.
Src: https://www.lucidchart.com/

## Sprint Reviews
Sprint 1 | x=done/not done
What we were supposed to do | What were we able to do | What we were not able to do
Set up Githup | X
SCRUM base | X
Decided what we do | X
Set up Eclipse | X
Set up MYSQL | X
Sprint 2 | x=done/not done
What we were supposed to do | What were we able to do | What we were not able to do
SQL connection | X
Admin login (form) | X
Admin login check |  | X
Create admin user and Encrypt password | X
Add question (form) |  | X
Add question to the database |  | X
Read questions from database (list) |  | X
add candidates |  | X
edit candidates |  | X
remove candidates |  | X
candidate can answer questions | X
candidate can edit their answers |  | X
Sprint 3 | x=done/not done
What we were supposed to do | What were we able to do | What we were not able to do
Admin login check | X
Admin can logout | X
Redirecting to admin page | X
Add question (form) |  | X
Add question to the database |  | X
Read questions from database (list) | X
add candidates |  | X
edit candidates |  | X
delete candidates |  | X
candidate can answer questions | x
candidate can edit their answers | x
Sprint 4 | x=done/not done
What we were supposed to do | What were we able to do | What we were not able to do
Pop-up information (x worked or not) | X
Style/UI (css) | X
Apply style to everything shown | X
Admin can logout | X
Add question (form) | X
Add question to the database | X
Edit question (form) | X
Update question to database | X
Confirmation of delete | X
Remove question from the database | X
add candidates | X
edit candidates | X
Confirmation of delete | X
remove candidates | X
add answers candidate questions | x
edit candidate questions answers | x

## sprint1
Sprint Backlog : Sprint 1
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5
Set up
Task: Set up Githup | 3 | All | Done |  |  |  |  | 2
Task: SCRUM base | 2 | All | Done |  |  |  |  | 3
Task: Decided what we do | 2 | All | Done |  |  |  |  | 1
Task: Set up Eclipse | 4 | All | Done | 4
Task: Set up MYSQL | 5 | All | Done |  |  |  |  | 2
TOTAL |  |  |  | 4 | 0 | 0 | 0 | 8

## sprint2
Sprint Backlog : Sprint 2
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | DAY 7
misc
Task: SQL connection | 5 | Sonja | Done |  |  | 4 | 2 |  |  | 1
as an admin I can log in
Task: Admin login (form) | 2 | Sonja | Done |  |  |  |  | 1
Task: Admin login check | 4 | Sonja | Inprogress |  |  |  |  | 3 | 1
Task: Create admin user and Encrypt password | 3 | Sonja | Done | [5 empty] | 2
as an admin I can add questions
Task: Add question (form) | 2 | Sonja | Inprogress
Task: Add question to the database | 4 | Sonja | Inprogress
as an admin I can see all the questions
Task: Read questions from database (list) | 2 | Sonja | Inprogress | [6 empty] | 2
as an admin I can add candidates
Task: add candidates | 5 | Kaisa | Inprogress | [5 empty] | 1 | 1
as an admin I can edit candidates
Task: edit candidates | 4 | Kaisa | Inprogress
as an admin I can remove candidates
Task: delete candidates | 3 | Kaisa | Inprogress
as an admin I can answer to candidates questions
Task: add answers candidate questions | 5 | Jenna | Done |  |  |  |  | 1 | 2
as an admin I can edit candidates questions
Task: edit candidate questions answers | 5 | Jenna | Inprogress
TOTAL |  |  |  | 0 | 0 | 4 | 2 | 5 | 6 | 4

## sprint3
Sprint Backlog : Sprint 3
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6
as an admin I can log in
Task: Admin login check | 4 | Sonja | Done |  |  |  | 2
Task: Admin can logout | 1 | Sonja | Inprogress |  |  |  |  | 1
Task: Redirecting to admin page | 3 | Sonja | Done |  |  |  |  | 3
as an admin I can add questions
Task: Add question (form) | 2 | Sonja | Inprogress
Task: Add question to the database | 4 | Sonja | Inprogress
as an admin I can see all the questions
Task: Read questions from database (list) | 2 | Sonja | Done |  |  | 2 | 2
as an admin I can add candidates
Task: add candidates | 5 | Kaisa | Inprogress |  |  |  | 3 |  | 6
as an admin I can edit candidates
Task: edit candidates | 4 | Kaisa | Inprogress |  |  |  | 2
as an admin I can remove candidates
Task: delete candidates | 3 | Kaisa | Inprogress |  |  |  | 1
as an admin I can answer to candidates questions
Task: add answers candidate questions | 5 | Jenna | Done
as an admin I can edit candidates questions
Task: edit candidate questions answers | 5 | Jenna | Done |  |  | 3 |  | 3
TOTAL |  |  |  | 0 | 0 | 5 | 10 | 7 | 6

## sprint4
Sprint Backlog : Sprint 4
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS | DAY 1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6
misc
Task: Pop-up information (x worked or not) | 2 | Sonja | Done |  |  |  |  | 1 | 2
Task: Style/UI (css) | 1 | Sonja | Done | [5 empty] | 3
Task: Apply style to everything shown | 1 | Sonja | Done | [5 empty] | 1
as an admin I can log in
Task: Admin can logout | 1 | Sonja | Done |  |  |  |  | 1
as an admin I can add questions
Task: Add question (form) | 2 | Sonja | Done |  | 2 | 1
Task: Add question to the database | 4 | Sonja | Done |  | 2 |  |  |  | 1
as an admin I can edit questions
Task: Edit question (form) | 2 | Sonja | Done |  |  | 2
Task: Update question to database | 4 | Sonja | Done |  |  | 3
as an admin I can delete questions
Task: Confirmation of delete | 2 | Sonja | Done | [5 empty] | 1
Task: Remove question from the database | 3 | Sonja | Done |  |  | 1
as an admin I can add candidates
Task: add candidates | 5 | Kaisa | Done |  |  | 5
as an admin I can edit candidates
Task: edit candidates | 4 | Kaisa | Done |  |  |  | 4
as an admin I can remove candidates
Task: Confirmation of delete | 2 | Sonja | Done | [5 empty] | 1
Task: remove candidates | 3 | Kaisa | Done | [5 empty] | 3
as an admin I can answer to candidates questions
Task: add answers candidate questions | 5 | Jenna | Done |  |  |  | 2 | 3
as an admin I can edit candidates questions
Task: edit candidate questions answers | 5 | Jenna | Done |  | 3 | 2
TOTAL |  |  |  | 0 | 7 | 14 | 6 | 5 | 12